## Sheet1
VL | ORIGINAL | FIX DO NAMING | FIND TEST | ASSUMPTION / FIX | OM | SDL | COST CENTRE | ZONE | SDL | OM | DO | Additional Note | Programme Original | Programme Actual | Day | Date | Has Site Been Contacted? | Has works been completed | Comments
CARDIFF NORTH DO | CARDIFF NORTH | CARDIFF NORTH DO | CARDIFF NORTH DO |  | OM Cardiff | C-SDL South Wales | 1110651 | C | C-SDL South Wales | OM Cardiff | CARDIFF NORTH DO |  | Week 1 | Week 1 | Thursday | 2020-07-02 | Yes | Yes
CHEPSTOW DO | CHEPSTOW | CHEPSTOW DO | CHEPSTOW DO |  | OM Newport | C-SDL South Wales | 1110659 | C | C-SDL South Wales | OM Newport | CHEPSTOW DO |  | Week 1 | Week 1 | Thursday | 2020-07-02 | Yes | Yes
PONTYPOOL DO | PONTYPOOL | PONTYPOOL DO | PONTYPOOL DO |  | OM Newport | C-SDL South Wales | 1110666 | C | C-SDL South Wales | OM Newport | PONTYPOOL DO |  | Week 1 | Week 1 | Thursday | 2020-07-02 | Yes | Yes
HEREFORD DO | HEREFORD | HEREFORD DO | HEREFORD DO |  | OM Hereford and Worcestershire | C-SDL Birmingham and HRWR | 1110195 | C | C-SDL Birmingham and HRWR | OM Hereford and Worcestershire | HEREFORD DO |  | Week 3 | Week 2 | Monday | 2020-07-06 | Yes | Yes
SUTTON COLDFIELD DO | SUTTON COLDFIELD | SUTTON COLDFIELD DO | SUTTON COLDFIELD DO |  | OM Birmingham Central | C-SDL Birmingham and HRWR | 1110019 | C | C-SDL Birmingham and HRWR | OM Birmingham Central | SUTTON COLDFIELD DO |  | Week 3 | Week 2 | Monday | 2020-07-06 | Yes | Yes
BICESTER DO | BICESTER | BICESTER DO | BICESTER DO |  | OM Thames Valley Central | C-SDL Thames Valley | 1110298 | C | C-SDL Thames Valley | OM Thames Valley Central | BICESTER DO |  | Week 2 | Week 2 | Monday | 2020-07-06 | Yes | Yes
SWINDON DO | SWINDON | SWINDON DO | SWINDON DO |  | OM Thames Valley West | C-SDL Thames Valley | 1118682 | C | C-SDL Thames Valley | OM Thames Valley West | SWINDON DO |  | Week 2 | Week 2 | Monday | 2020-07-06 | Yes | Yes
GLOUCESTER SOUTH DO | GLOUCESTER SOUTH | GLOUCESTER SOUTH DO | GLOUCESTER SOUTH DO |  | OM Gloucester | C-SDL West England | 1110193 | C | C-SDL West England | OM Gloucester | GLOUCESTER SOUTH DO |  | Week 1 | Week 2 | Monday | 2020-07-06 | Yes | Yes
SWINDON DO (DORCAN) | SWINDON DO (DORCAN) | SWINDON DO (DORCAN) | #N/A | Swindon west or just DO? | #N/A | #N/A | #N/A | C | C-SDL Thames Valley | OM TV West | SWINDON DO (DORCAN) |  | Week 2 | Week 2 | Monday | 2020-07-06 | Yes | Yes
Swindon MC | [7 empty] | C | C-Thames Valley | Thames Valley | Swindon MC |  | Week 2 | Week 2 | Monday | 2020-07-06 | Yes | Yes
NEWCASTLE UNDER LYME DO | NEWCASTLE UNDER LYME | NEWCASTLE UNDER LYME DO | NEWCASTLE UNDER LYME DO |  | OM Stoke Telford Walsall | C-SDL North West Midlands | 1110248 | C | C-SDL North West Midlands | OM Stoke Telford Walsall | NEWCASTLE UNDER LYME DO |  | Week 3 | Week 2 | Tuesday | 2020-07-07 | Yes | Yes
STAFFORD DO | STAFFORD | STAFFORD DO | STAFFORD DO |  | OM Stoke Telford Walsall | C-SDL North West Midlands | 1110249 | C | C-SDL North West Midlands | OM Stoke Telford Walsall | STAFFORD DO |  | Week 3 | Week 2 | Tuesday | 2020-07-07 | Yes | Yes
BRISTOL SOUTH EAST DO | BRISTOL SOUTH EAST DO | BRISTOL SOUTH EAST DO | BRISTOL SOUTH EAST DO |  | OM Bristol South and West Somerset | C-SDL West England | 1110595 | C | C-SDL West England | OM Bristol South and West Somerset | BRISTOL SOUTH EAST DO |  | Week 1 | Week 2 | Tuesday | 2020-07-07 | Yes | Yes
TAUNTON DO | TAUNTON DO | TAUNTON DO | TAUNTON DO |  | OM Bristol South and West Somerset | C-SDL West England | 1110567 | C | C-SDL West England | OM Bristol South and West Somerset | TAUNTON DO |  | Week 1 | Week 2 | Tuesday | 2020-07-07 | Yes | Yes
WESTON SUPER MARE DO | WESTON SUPER MARE DO | WESTON SUPER MARE DO | WESTON SUPER MARE DO |  | OM Bristol South and West Somerset | C-SDL West England | 1110617 | C | C-SDL West England | OM Bristol South and West Somerset | WESTON SUPER MARE DO |  | Week 1 | Week 2 | Tuesday | 2020-07-07 | Yes | Yes
MACCLESFIELD DO | MACCLESFIELD | MACCLESFIELD DO | MACCLESFIELD DO |  | OM Stockport | N-SDL Greater Manchester | 1112981 | N | N-SDL Greater Manchester | OM Stockport | MACCLESFIELD DO |  | Week 2 | Week 2 | Tuesday | 2020-07-07 | Yes | Yes
HATFIELD DO | HATFIELD | HATFIELD DO | #N/A | Is this AL or DN | #N/A | #N/A | #N/A | C | C-SDL Home Counties South | OM SW London Central | HATFIELD DO |  | Week 1 | Week 3 | Tuesday | 2020-07-07 | Yes | Yes
SHEFFIELD NORTH DO | SHEFFIELD NORTH DO | SHEFFIELD NORTH DO | SHEFFIELD NORTH DO | name changed from SHEFFIELD N DO | OM Sheffield North | C-SDL South Yorks and Lincs | 1112909 | C | C-SDL South Yorks and Lincs | OM Sheffield North | SHEFFIELD NORTH DO |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
Sheffield MC | [7 empty] | C | C-SDL South Yorks and Lincs | South Yorks & Lincs | Sheffield MC |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
MANCHESTER SOUTH EAST DO | MANCHESTER SOUTH EAST | MANCHESTER SOUTH EAST DO | MANCHESTER SOUTH EAST DO | name changed from MANCHESTER SEDO | OM Manchester | N-SDL Greater Manchester | 1112807 | N | N-SDL Greater Manchester | OM Manchester | MANCHESTER SOUTH EAST DO |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
MANCHESTER SOUTH DO | MANCHESTER SOUTH DO | MANCHESTER SOUTH DO | MANCHESTER SOUTH DO |  | OM Manchester | N-SDL Greater Manchester | 1112805 | N | N-SDL Greater Manchester | OM Manchester | MANCHESTER SOUTH DO |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
MANCHESTER SOUTH WEST DO | MANCHESTER SOUTH WEST | MANCHESTER SOUTH WEST DO | MANCHESTER SOUTH WEST DO | name changed from MANCHESTER SW | OM Manchester | N-SDL Greater Manchester | 1112811 | N | N-SDL Greater Manchester | OM Manchester | MANCHESTER SOUTH WEST DO |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
STOCKPORT CENTRAL DO | STOCKPORT CENTRAL DO | STOCKPORT CENTRAL DO | STOCKPORT CENTRAL DO |  | OM Stockport | N-SDL Greater Manchester | 1112958 | N | N-SDL Greater Manchester | OM Stockport | STOCKPORT CENTRAL DO |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
Chester MC | [7 empty] | N | N-SDL Cheshire & Merseyside | Cheshire & Merseyside | Chester MC |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
Manchester | [7 empty] | N | N-SDL Manchester | Manchester | Manchester |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
Warrington MC | [7 empty] | N | N-SDL - Merseyside | Merseyside | Warrington MC |  | Week 2 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
WEYMOUTH DO | WEYMOUTH | WEYMOUTH DO | WEYMOUTH DO |  | OM SC North | S-SDL South Coast | 1110530 | S | S-SDL South Coast | OM SC North | WEYMOUTH DO |  | Week 1 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
BOURNEMOUTH DO | BOURNEMOUTH | BOURNEMOUTH DO | BOURNEMOUTH DO |  | OM SC West | S-SDL South Coast | 1110512 | S | S-SDL South Coast | OM SC West | BOURNEMOUTH DO |  | Week 1 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
RINGWOOD DO | RINGWOOD | RINGWOOD DO | RINGWOOD DO |  | OM SC West | S-SDL South Coast | 1110522 | S | S-SDL South Coast | OM SC West | RINGWOOD DO |  | Week 1 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
WINTON DO | [7 empty] | S | S-SDL South Coast | OM West | WINTON DO |  | Week 1 | Week 2 | Wednesday | 2020-07-08 | Yes | Yes
NARBETH DO | NARBETH DO | NARBETH DO | #N/A | no name in hierarchy | #N/A | #N/A | #N/A | C | C- SDL South Wales | OM Swansea | NARBETH DO |  | Week 1 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
LLANGEFNI DO | LLANGEFNI | LLANGEFNI DO | LLANGEFNI DO |  | OM North Wales | N-SDL Chester and North Wales | 1110093 | N | N-SDL Chester and North Wales | OM North Wales | LLANGEFNI DO |  | Week 2 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
BLACKPOOL DO | BLACKPOOL | BLACKPOOL DO | BLACKPOOL DO |  | OM Blackburn and Fylde | N-SDL Cumbria | 1112867 | N | N-SDL Cumbria | OM Blackburn and Fylde | BLACKPOOL DO |  | Week 1 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
OLDHAM DO | OLDHAM | OLDHAM DO | OLDHAM DO |  | OM East Pennines | N-SDL Greater Manchester | 1112821 | N | N-SDL Greater Manchester | OM East Pennines | OLDHAM DO |  | Week 2 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
ROCHDALE DO | ROCHDALE | ROCHDALE DO | ROCHDALE DO |  | OM East Pennines | N-SDL Greater Manchester | 1112823 | N | N-SDL Greater Manchester | OM East Pennines | ROCHDALE DO |  | Week 2 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
BITTERNE MANOR DO | BITTERNE MANOR | BITTERNE MANOR DO | BITTERNE MANOR DO |  | OM SC Central | S-SDL South Coast | 1110954 | S | S-SDL South Coast | OM SC Central | BITTERNE MANOR DO |  | Week 1 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
SHIRLEY SO DO | SHIRLEY SO DO | SHIRLEY SO DO | SHIRLEY SO DO |  | OM SC Central | S-SDL South Coast | 1110955 | S | S-SDL South Coast | OM SC Central | SHIRLEY SO DO |  | Week 1 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
PORTSMOUTH DO | PORTSMOUTH DO | PORTSMOUTH DO | PORTSMOUTH DO |  | OM SC East | S-SDL South Coast | 1110977 | S | S-SDL South Coast | OM SC East | PORTSMOUTH DO |  | Week 1 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
GATWICK MC | [7 empty] | S | S-SDL South East | South East | GATWICK MC |  | Week 3 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
COLCHESTER DO | COLCHESTER | COLCHESTER DO | COLCHESTER DO |  | OM North Essex | S-SDL Essex and South Anglia | 1111107 | S | S-SDL Essex and South Anglia | OM North Essex | COLCHESTER DO |  | Week 3 | Week 2 | Thursday | 2020-07-09 | Yes | Yes | Screen fitted and site have erected own installation during Covid period. SHE advice required if to stay or be removed.
CLACTON ON SEA DO | CLACTON ON SEA | CLACTON ON SEA DO | CLACTON ON SEA DO |  | OM South Anglia | S-SDL Essex and South Anglia | 1111106 | S | S-SDL Essex and South Anglia | OM South Anglia | CLACTON ON SEA DO |  | Week 3 | Week 2 | Thursday | 2020-07-09 | Yes | Yes
[8 empty] | S | C- SDL West of England | OM Bristol South and West Somerset | NAILSEA DO |  | Week 2 | Week 2 | Thursday | 2020-07-09 | Yes | NO | Design issue - proposal provided to SHE team and awaiting feedback on way forward. Will be moved to Week 3
BRISTOL MC | [7 empty] | C | C-SDL West England | West England | BRISTOL MC |  | Week 1 | Week 2 | Friday | 2020-07-10 | Yes | Yes | Redesign of screen as glass counter top.
HCN MC | [7 empty] | C | C-Home Counties North | HCN | HCN MC |  | Week 2 | Week 2 | Friday | 2020-07-10 | Yes | Yes
WIDNES DO | WIDNES DO | WIDNES DO | WIDNES DO |  | OM Wigan | N-SDL Merseyside | 1112558 | N | N-SDL Merseyside | OM Wigan | WIDNES DO |  | Week 2 | Week 2 | Friday | 2020-07-10 | Yes | Yes
CAMBERLEY DO | CAMBERLEY | CAMBERLEY DO | CAMBERLEY DO |  | OM HCS West | S-SDL Home Counties South | 1110780 | S | S-SDL Home Counties South | OM HCS West | CAMBERLEY DO |  | Week 2 | Week 2 | Friday | 2020-07-10 | Yes | Yes
GUILDFORD DO | GUILDFORD | GUILDFORD DO | GUILDFORD DO |  | OM HCS West | S-SDL Home Counties South | 1110795 | S | S-SDL Home Counties South | OM HCS West | GUILDFORD DO |  | Week 2 | Week 2 | Friday | 2020-07-10 | Yes | Yes
CAMBRIDGE DO | CAMBRIDGE | CAMBRIDGE DO | CAMBRIDGE DO |  | OM Norfolk | C-SDL Anglia | 1111051 | C | C-SDL Anglia | OM Norfolk | CAMBRIDGE DO |  | Week 3 | Week 2 | Friday | 2020-07-10 | Yes | Yes
ST ALBANS DO | ST ALBANS | ST ALBANS DO | ST ALBANS DO |  | OM HCN Central | C-SDL Home Counties North | 1111706 | C | C-SDL Home Counties North | OM HCN Central | ST ALBANS DO |  | Week 2 | Week 2 | Friday | 2020-07-10 | Yes | Yes
Inverness MC | [7 empty] | N | N-SDL North Scotland | North Scotland | Inverness MC |  | Week 1 | Week 2 | Friday | 2020-07-10 | Yes | Yes
ORTON SOUTHGATE DO | ORTON SOUTHGATE | ORTON SOUTHGATE DO | ORTON SOUTHGATE DO | name changed from ORTON SOUTHGATE (PE) | OM Peterborough | C-SDL Anglia | 1111413 | C | C-SDL Anglia | OM Peterborough | ORTON SOUTHGATE DO |  | Week 3 | Week 2 | Saturday | 2020-07-11 | Yes
Peterborough M/C | [7 empty] | C | C-SDL Anglia | Anglia | Peterborough M/C |  | Week 3 | Week 2 | Saturday | 2020-07-11 | Yes |  | Refusing installation - passed to SHE advisor for advice on way forward
South Midlands MC | [7 empty] | C | C-South Midlands | South Midlands | South Midlands MC |  | Week 3 | Week 2 | Saturday | 2020-07-11 | Yes |  | Refusing installation - passed to SHE advisor for advice on way forward
Edinburgh MC | [7 empty] | N | N-SDL East Of Scotland | East Of Scotland | Edinburgh MC |  | Week 1 | Week 2 | Saturday | 2020-07-11 | Yes |  | Screen arrived no brackets - fitted Saturday 11th July
GLAISDALE PARKWAY DO | GLAISDALE PARKWAY DO | GLAISDALE PARKWAY DO | GLAISDALE PARKWAY DO |  | OM Nottinghamshire | C-SDL East Midlands | 1111347 | C | C-SDL East Midlands | OM Nottinghamshire | GLAISDALE PARKWAY DO |  | Week 2 | Week 3 | Monday | 2020-07-13 | Yes
LEEDS CITY DO | LEEDS CITY DO | LEEDS CITY DO | LEEDS CITY DO |  | OM Central Yorkshire | N-SDL Yorkshire | 1112691 | N | N-SDL Yorkshire | OM Central Yorkshire | LEEDS CITY DO |  | Week 2 | Week 3 | Monday | 2020-07-13 | Yes
WAKEFIELD DO | WAKEFIELD | WAKEFIELD DO | WAKEFIELD DO |  | OM Greater Yorkshire | N-SDL Yorkshire | 1112717 | N | N-SDL Yorkshire | OM Greater Yorkshire | WAKEFIELD DO |  | Week 2 | Week 3 | Monday | 2020-07-13 | Yes
Leeds MC | [7 empty] | N | N-SDL Yorkshire | Yorkshire | Leeds MC |  | Week 1 | Week 3 | Monday | 2020-07-13 | Yes |  | Already in place???? SHE to confirm if required.
BROMLEY DO | BROMLEY DO | BROMLEY DO | BROMLEY DO |  | OM SE London East | S-SDL South East London | 1111725 | S | S-SDL South East London | OM SE London East | BROMLEY DO |  | Week 3 | Week 3 | Monday | 2020-07-13 | Yes
CROYDON DO | CROYDON | CROYDON DO | CROYDON DO |  | OM SE London South | S-SDL South East London | 1111733 | S | S-SDL South East London | OM SE London South | CROYDON DO |  | Week 3 | Week 3 | Monday | 2020-07-13 | Yes
FOREST HILL DO | FOREST HILL | FOREST HILL DO | FOREST HILL DO |  | OM SE London West | S-SDL South East London | 1111572 | S | S-SDL South East London | OM SE London West | FOREST HILL DO |  | Week 3 | Week 3 | Monday | 2020-07-13 | Yes
CROYDON MC | [7 empty] | S | S-SDL South East London | South East London | CROYDON MC |  | Week 3 | Week 3 | Monday | 2020-07-13 | Yes
MEDWAY MC | [7 empty] | S | S-SDL Medway | Medway | MEDWAY MC |  | Week 3 | Week 3 | Monday | 2020-07-13 | Yes
CARNFORTH DO | CARNFORTH | CARNFORTH DO | CARNFORTH DO |  | OM Lancaster | N-SDL Cumbria | 1112878 | N | N-SDL Cumbria | OM Lancaster | CARNFORTH DO |  | Week 1 | Week 3 | Tuesday | 2020-07-14 | Yes
CHORLEY DO | CHORLEY | CHORLEY DO | CHORLEY DO |  | OM Preston | N-SDL Cumbria | 1112843 | N | N-SDL Cumbria | OM Preston | CHORLEY DO |  | Week 1 | Week 3 | Tuesday | 2020-07-14 | Yes
PRESTON CENTRAL DO | PRESTON CENTRAL DO | PRESTON CENTRAL DO | PRESTON CENTRAL DO |  | OM Preston | N-SDL Cumbria | 1112849 | N | N-SDL Cumbria | OM Preston | PRESTON CENTRAL DO |  | Week 1 | Week 3 | Tuesday | 2020-07-14 | Yes
BRADFORD NORTH DO | BRADFORD NORTH DO | BRADFORD NORTH DO | BRADFORD NORTH DO |  | OM West Yorkshire | N-SDL Yorkshire | 1112487 | N | N-SDL Yorkshire | OM West Yorkshire | BRADFORD NORTH DO |  | Week 2 | Week 3 | Tuesday | 2020-07-14 | Yes
CLAPHAM DO | CLAPHAM | CLAPHAM DO | CLAPHAM DO |  | OM South West London | S-SDL Home Counties South | 1111580 | S | S-SDL Home Counties South | OM South West London | CLAPHAM DO |  | Week 2 | Week 3 | Tuesday | 2020-07-14 | Yes |  | Screen already in place - SHE to confirm site to be removed from programme
STREATHAM DO | STREATHAM | STREATHAM DO | STREATHAM DO |  | OM SW London Central | S-SDL Home Counties South | 1111594 | S | S-SDL Home Counties South | OM SW London Central | STREATHAM DO |  | Week 2 | Week 3 | Tuesday | 2020-07-14 | Yes
ROMFORD MC | [7 empty] | S | S-SDL Central and East London | Central and East London | ROMFORD MC |  | Week 3 | Week 3 | Tuesday | 2020-07-14 | Yes
BALHAM DO | BALHAM | BALHAM DO | BALHAM DO |  | OM South West London | S-SDL Home Counties South | 1111590 | S | S-SDL Home Counties South | OM South West London | BALHAM DO |  | Week 2 | Week 3 | Tuesday | 2020-07-14 | Yes
BATTERSEA DO | BATTERSEA | BATTERSEA DO | BATTERSEA DO |  | OM South West London | S-SDL Home Counties South | 1111589 | S | S-SDL Home Counties South | OM South West London | BATTERSEA DO |  | Week 2 | Week 3 | Tuesday | 2020-07-14 | Yes
LEICESTER DO | LEICESTER | LEICESTER DO | #N/A | is this east, north or south | #N/A | #N/A | #N/A | C | C-SDL South Mids | OM North Leicestershire | LEICESTER DO |  | Week 3 | Week 3 | Tuesday | 2020-07-14 | Yes |  | Screen delivery delayed - installation now Week 3
NORTH TYNESIDE DO | NORTH TYNESIDE DO | NORTH TYNESIDE DO | NORTH TYNESIDE DO |  | OM Newcastle | N-SDL North East | 1112424 | N | N-SDL North East | OM Newcastle | NORTH TYNESIDE DO |  | Week 1 | Week 3 | Wednesday | 2020-07-15 | Yes
SOUTH SHIELDS DO | SOUTH SHIELDS | SOUTH SHIELDS DO | SOUTH SHIELDS DO |  | OM Sunderland and Durham | N-SDL North East | 1112416 | N | N-SDL North East | OM Sunderland and Durham | SOUTH SHIELDS DO |  | Week 1 | Week 3 | Wednesday | 2020-07-15 | Yes
NEWCASTLE WEST DO | WEST 5 | WEST 5 DO | #N/A | no name in hierarchy | #N/A | #N/A | #N/A | N | N-SDL North East | OM Newcastle | NEWCASTLE WEST DO |  | Week 1 | Week 3 | Wednesday | 2020-07-15 | Yes
Newcastle MC | [7 empty] | N | N-SDL - North East | North East | Newcastle MC |  | Week 1 | Week 3 | Wednesday | 2020-07-15 | Yes
WEST BROMPTON DO | WEST BROMPTON | WEST BROMPTON DO | WEST BROMPTON DO |  | OM South West London | S-SDL Home Counties South | 1111586 | S | S-SDL Home Counties South | OM South West London | WEST BROMPTON DO |  | Week 2 | Week 3 | Wednesday | 2020-07-15 | Yes
FULHAM DO | FULHAM | FULHAM DO | FULHAM DO |  | OM SW London Central | S-SDL Home Counties South | 1111582 | S | S-SDL Home Counties South | OM SW London Central | FULHAM DO |  | Week 2 | Week 3 | Wednesday | 2020-07-15 | Yes
DUNDEE CENTRAL DO | DUNDEE CENTRAL | DUNDEE CENTRAL DO | DUNDEE CENTRAL DO |  | OM EOS North | N-SDL East Scotland | 1112167 | N | N-SDL East Scotland | OM EOS North | DUNDEE CENTRAL DO |  | Week 1 | Week 3 | Wednesday | 2020-07-15 | Yes |  | Screen delivery delayed - installation now Week 3
EDINBURGH EAST DO | EDINBURGH EAST | EDINBURGH EAST DO | EDINBURGH EAST DO |  | OM EOS Edinburgh City | N-SDL East Scotland | 1112206 | N | N-SDL East Scotland | OM EOS Edinburgh City | EDINBURGH EAST DO |  | Week 1 | Week 3 | Wednesday | 2020-07-15 | Yes |  | Screen delivery delayed - installation now Week 3
Aberdeen MC | [7 empty] | N | N-SDL North Scotland | North Scotland | Aberdeen MC |  | Week 1 | Week 3 | Wednesday | 2020-07-15 | Yes |  | Screen delivery delayed - installation now Week 3
Glasgow MC | [7 empty] | N | N-SDL West Of Scotland | West Of Scotland | Glasgow MC |  | Week 1 | Week 3 | Wednesday | 2020-07-15 | Yes |  | Screen delivery delayed - installation now Week 3
PUTNEY DO | PUTNEY | PUTNEY DO | PUTNEY DO |  | OM South West London | S-SDL Home Counties South | 1111593 | S | S-SDL Home Counties South | OM South West London | PUTNEY DO |  | Week 2 | Week 3 | Wednesday | 2020-07-15 | Yes
TOOTING DO | TOOTING | TOOTING DO | TOOTING DO |  | OM South West London | S-SDL Home Counties South | 1111595 | S | S-SDL Home Counties South | OM South West London | TOOTING DO |  | Week 2 | Week 3 | Wednesday | 2020-07-15 | Yes
WIMBLEDON DO | WIMBLEDON | WIMBLEDON DO | WIMBLEDON DO |  | OM SW London Central | S-SDL Home Counties South | 1111597 | S | S-SDL Home Counties South | OM SW London Central | WIMBLEDON DO |  | Week 2 | Week 3 | Wednesday | 2020-07-15 | Yes
DARLINGTON DO | DARLINGTON | DARLINGTON DO | DARLINGTON DO |  | OM Tees Valley | N-SDL North East | 1112105 | N | N-SDL North East | OM Tees Valley | DARLINGTON DO | awkward shape (sort of S-shape; have a photo if needed) | Week 1 | Week 3 | Thursday | 2020-07-16 | Yes
DERWENTSIDE DO | DERWENTSIDE | DERWENTSIDE DO | DERWENTSIDE DO |  | OM Sunderland and Durham | N-SDL North East | 1112117 | N | N-SDL North East | OM Sunderland and Durham | DERWENTSIDE DO |  | Week 1 | Week 3 | Thursday | 2020-07-16 | Yes
DURHAM DO | DURHAM | DURHAM DO | DURHAM DO |  | OM Sunderland and Durham | N-SDL North East | 1112116 | N | N-SDL North East | OM Sunderland and Durham | DURHAM DO |  | Week 1 | Week 3 | Thursday | 2020-07-16 | Yes
SUNDERLAND DO | SUNDERLAND | SUNDERLAND DO | SUNDERLAND DO |  | OM Sunderland and Durham | N-SDL North East | 1112407 | N | N-SDL North East | OM Sunderland and Durham | SUNDERLAND DO |  | Week 1 | Week 3 | Thursday | 2020-07-16 | Yes
BRENTFORD DO | BRENTFORD | BRENTFORD DO | BRENTFORD DO |  | OM HCS North East | S-SDL Home Counties South | 1111823 | S | S-SDL Home Counties South | OM HCS North East | BRENTFORD DO |  | Week 2 | Week 3 | Thursday | 2020-07-16 | Yes
CRICKLEWOOD DO | CRICKLEWOOD DO | CRICKLEWOOD DO | CRICKLEWOOD DO |  | OM NW London | S-SDL Greater London | 1111519 | S | S-SDL Greater London | OM NW London | CRICKLEWOOD DO |  | Week 3 | Week 3 | Thursday | 2020-07-16 | Yes
GOLDERS GREEN DO | GOLDERS GREEN | GOLDERS GREEN DO | GOLDERS GREEN DO |  | OM NW London | S-SDL Greater London | 1111528 | S | S-SDL Greater London | OM NW London | GOLDERS GREEN DO |  | Week 3 | Week 3 | Thursday | 2020-07-16 | Yes
WEMBLEY DO | WEMBLEY | WEMBLEY DO | #N/A | Wembley highs or lows do? | #N/A | #N/A | #N/A | S | S - SDL Greater London | OM HCS North | WEMBLEY DO |  | Week 3 | Week 3 | Thursday | 2020-07-16 | Yes
GREENFORD MC | [7 empty] | S | S-SDL Greater London | Greater London | GREENFORD MC |  | Week 3 | Week 3 | Thursday | 2020-07-16 | Yes
HULL MALMO ROAD DO | HULL MALMO ROAD DO | HULL MALMO ROAD DO | HULL MALMO ROAD DO |  | OM E Yorks and Lincs | C-SDL South Yorks and Lincs | 1112595 | C | C-SDL South Yorks and Lincs | OM E Yorks and Lincs | HULL MALMO ROAD DO |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes
MIDDLESBROUGH DO | MIDDLESBROUGH | MIDDLESBROUGH DO | MIDDLESBROUGH DO |  | OM Tees Valley | N-SDL North East | 1112091 | N | N-SDL North East | OM Tees Valley | MIDDLESBROUGH DO | currently have a low screen - up to chest level | Week 1 | Week 3 | Friday | 2020-07-17 | Yes
YORK CENTRAL DO | YORK CENTRAL | YORK CENTRAL DO | YORK CENTRAL DO | name changed from YORK DO | OM Greater Yorkshire | N-SDL Yorkshire | 1112997 | N | N-SDL Yorkshire | OM Greater Yorkshire | YORK CENTRAL DO |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes
STOCKTON DO | STOCKTON | STOCKTON DO | #N/A | is this 'on tees' or brook? | #N/A | #N/A | #N/A | N | N-SDL-North East | OM Tees Valley | STOCKTON DO |  | Week 1 | Week 3 | Friday | 2020-07-17 | Yes
[8 empty] | S | South Yorkshire & Lincolnshire | OM North Lincolnshire | Grimsby DO |  | Late additon | Week 3 | Friday | 2020-07-17 | Yes
[8 empty] | S | South Yorkshire & Lincolnshire | OM North Lincolnshire | Doncaster DO |  | Late additon | Week 3 | Friday | 2020-07-17 | Yes
SKEGNESS DO | SKEGNESS | SKEGNESS DO | SKEGNESS DO |  | OM Peterborough | C-SDL Anglia | 1111387 | C | C-SDL Anglia | OM Peterborough | SKEGNESS DO |  | Week 3 | Week 3 | Friday | 2020-07-17 | Yes
LEIGHTON BUZZARD DO | LEIGHTON BUZZARD | LEIGHTON BUZZARD DO | LEIGHTON BUZZARD DO |  | OM HCN East | C-SDL Home Counties North | 1111228 | C | C-SDL Home Counties North | OM HCN East | LEIGHTON BUZZARD DO |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes
KIRKBY DO | KIRKBY | KIRKBY DO | KIRKBY DO |  | OM Wigan | N-SDL Merseyside | 1112766 | N | N-SDL Merseyside | OM Wigan | KIRKBY DO |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes |  | Withdrawn
ANTRIM DO | ANTRIM | ANTRIM DO | ANTRIM DO |  | OM NI West | N-SDL Northern Ireland | 1112022 | N | N-SDL Northern Ireland | OM NI West | ANTRIM DO |  | Week 1 | Week 3 | Friday | 2020-07-17 | Yes |  | Screen delivery delayed - installation now Week 3
OMAGH DO | OMAGH | OMAGH DO | OMAGH DO |  | OM NI West | N-SDL Northern Ireland | 1112030 | N | N-SDL Northern Ireland | OM NI West | OMAGH DO |  | Week 1 | Week 3 | Friday | 2020-07-17 | Yes |  | Screen delivery delayed - installation now Week 3
STRABANE DO | STRABANE DO | STRABANE DO | STRABANE DO |  | OM NI West | N-SDL Northern Ireland | 1112028 | N | N-SDL Northern Ireland | OM NI West | STRABANE DO |  | Week 1 | Week 3 | Friday | 2020-07-17 | Yes |  | Screen delivery delayed - installation now Week 3
Northern Ireland MC | [7 empty] | N | N-SDL - Northern Ireland | Northern Ireland | Northern Ireland MC |  | Week 1 | Week 3 | Friday | 2020-07-17 | Yes |  | Screen delivery delayed - installation now Week 3
Carlisle MC | [7 empty] | N | N-SDL - Cumbria | Cumbria | Carlisle MC |  | Week 1 | Week 3 | Friday | 2020-07-17 | Yes
HAYES DO | HAYES DO | HAYES DO | HAYES DO |  | OM Harrow and Uxbridge | S-SDL Greater London | 1110856 | S | S-SDL Greater London | OM Harrow and Uxbridge | HAYES DO |  | Week 3 | Week 3 | Friday | 2020-07-17 | Yes
HOUNSLOW DO | Hounslow DO | Hounslow DO | HOUNSLOW DO |  | OM HCS North East | S-SDL Home Counties South | 1111826 | S | S-SDL Home Counties South | OM HCS North East | HOUNSLOW DO |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes
STAINES DO | STAINES DO | STAINES DO | STAINES DO |  | OM HCS North East | S-SDL Home Counties South | 1111828 | S | S-SDL Home Counties South | OM HCS North East | STAINES DO |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes
MOLESEY DO | MOLESEY | MOLESEY DO | MOLESEY DO | name changed from MOLESEY EAST | OM HCS North West | S-SDL Home Counties South | 1111845 | S | S-SDL Home Counties South | OM HCS North West | MOLESEY DO |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes
ISLINGTON DO | ISLINGTON | ISLINGTON DO | ISLINGTON DO |  | OM North London | S-SDL Central London | 1111486 | S | S-SDL Central London | OM North London | ISLINGTON DO |  | Week 3 | Week 3 | Friday | 2020-07-17 | Yes
DEBDEN DO | DEBDEN | DEBDEN DO | DEBDEN DO |  | OM South Essex | S-SDL East London | 1111666 | S | S-SDL East London | OM South Essex | DEBDEN DO |  | Week 3 | Week 3 | Friday | 2020-07-17 | Yes
CHELMSFORD DO | CHELMSFORD | CHELMSFORD DO | CHELMSFORD DO |  | OM West Essex | S-SDL Essex and South Anglia | 1111098 | S | S-SDL Essex and South Anglia | OM West Essex | CHELMSFORD DO |  | Week 3 | Week 3 | Friday | 2020-07-17 | Yes
WESTBOURNE PARK DO | WESTBOURNE PARK | WESTBOURNE PARK DO | #N/A | is this Westbourne do? | #N/A | #N/A | #N/A | S | S - SDL Greater London | OM West London and Slough | WESTBOURNE PARK DO | This seems to be WLDC, which is also called Queensway CSP | Week 3 | Week 3 | Friday | 2020-07-17 | Yes
MOUNT PLEASANT MC | [7 empty] | S | S-SDL Central and East London | Central and East London | MOUNT PLEASANT MC |  | Week 3 | Week 3 | Friday | 2020-07-17 | Yes
CHELMSFORD MC | [7 empty] | S | S-SDL Essex and South Anglia | Essex and South Anglia | CHELMSFORD MC |  | Week 3 | Week 3 | Friday | 2020-07-17 | Yes
JUBILEE MC | [7 empty] | S | S-SDL Home Counties South | Home Counties South | JUBILEE MC |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes
HAYLE DO | [7 empty] | S | S-SDL South West | OM West Cornwall | HAYLE DO |  | Late additon | Week 3 | Friday | 2020-07-17 | Yes
EASTLEIGH DO | [7 empty] | S | S-SDL South Coast | OM SC Central | EASTLEIGH DO |  | Late additon | Week 3 | Friday | 2020-07-17 | Yes
[9 empty] | S-SDL Central and East London | Central and East London | West End CSP |  | Late additon | Week 3 | Friday | 2020-07-17 | Yes
[9 empty] | OM West London and Slough | West London Delivery Centre | West London DO |  | Week 2 | Week 3 | Friday | 2020-07-17 | Yes |  | Clarification required on office address as WLDC has no reception or CSP. Options: Askew Road CSP - Not open plan counter Westbourne Grove CSP - covered as above Harrow Road CSP - open plan desk SHE to advise on way forward
Norwich M/C | [7 empty] | C | C-SDL Anglia | Anglia | Norwich M/C |  | Week 3 | Week 3 | TBC | TBC | Yes | Yes | Screen already in place - SHE reviewing. Will be Week 3 if to be progressed

## Sheet2
Yes
No