## Version control
| Name | Version No. | Changes
13th Dec 2011 | Howard Bedwell | 0.1 | Initial version
14th Dec 2011 | Howard Bedwell | 0.2 | Supporting document task names changed for the Flow meeting (19 Dec 2011)
16th Dec 2011 | Howard Bedwell | 0.3 | Updated
16th Dec 2011 | Howard Bedwell | 0.4-5 | Updated to reflect Sharepoint
23rd Dec 2011 | Shaun England | 1 | Updated to reflect feedback from Flow Leads
9th Jan 2012 | Howard Bedwell | 1.1 | Updated after feeback from CWU and Safety Director
11th Jan 2012 | Howard Bedwell | 1.2 | Updated to reflect changes made in ACP workshop - NDC drawings request moved to Activity order 1 & Week '-22' added to timeline - 2 X Flow activity orders merged so Task numbers from 22 down have changed to reflect this.
16th Jan 2012 | Howard Bedwell | 1.3 | Updated to match up with the ACP tasks - changed flow activity order 21 to -8 weeks from -9
19th Jan 2012 | Howard Bedwell | 1.4 | ACP Task numbers added to column
23rd Jan 2012 | Howard Bedwell | 1.5 | NDC Drawing request updated to reflect new procedure
26th Jan 2012 | Howard Bedwell | 1.6 | Brought in Line with ACP - Gleeds Milestones and Safety Concurrence.
2nd Feb 2012 | Mark Hoggar | 1.7 | Updated to align with Joint Indoor Work Method Guidance agreement

## Instructions
Insert the date of your planned outdoor revision in cell AJ2 and the dates will automatically populate

## Indoor work method imp Gannt
Indoor work method improvement activity order | ACP Task number /original task number | Gleeds tracking mile-stone | ACP Ref No. | ACP Task / Activity | Detail | Supporting Document | Supporting Document | Supporting Document | Supporting Document | Supporting Document | Owner | Support | Duration Hours | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | Indoor weekend of change | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | Outdoor 1st Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
[14 empty] | 2011-07-13 | 2011-07-20 | 2011-07-27 | 2011-08-03 | 2011-08-10 | 2011-08-17 | 2011-08-24 | 2011-08-31 | 2011-09-07 | 2011-09-14 | 2011-09-21 | 2011-09-28 | 2011-10-05 | 2011-10-12 |  | 2011-10-19 | 2011-10-26 | 2011-11-02 | 2011-11-09 | 2011-11-16 | 2011-11-23 | 2011-11-30 | 2011-12-07 | 2011-12-14 | 2011-12-21 | 2011-12-28 | 2012-01-04 | 2012-01-11 | 2012-01-18 | 2012-01-25 | 2012-02-01 | 2012-02-08
1 | 15 | N/A | 8 | Get the unit ready for all the Indoor changes (Site Preparation) | Download the Site Drawings from the Gleedsspace Sharepoint site - If not on there then requests to be sent to: shelly.humphreys@leeds-ndc-uk.co.uk; regan.coulsen@leeds-ndc-uk.co.uk | http://www.gleedsspace.com/CA/RM/default.aspx |  |  |  |  | Project Manager | NDC | 1
2 | 15 | N/A | 14 | Get the unit ready for all the Indoor changes (Site Preparation) | Office 'Indoor work method start up' meeting. Understand the Indoor work method scope and understand the timeline (this Gantt Chart). Complete the Delivery Office Site inspection & ensure that NDC drawing matches the site 'reality' | Task 09e - Indoor work method improvemnt Gantt Chart [R].xls | Task 09f - DP Indoor work methods Scope and Assets [R] | Task 14b - DP Delivery Office Site Inspection [CA] | Tasks 14c & 14 e - DP Indoor work method improvement Principles Overview v3 [R] and Safety Concurrence Slide pack [R] | Task 14f - Royal Mail & CWU Indoor work metods v1 1st Febuary 2012 | Project Manager | Planner / DOM / CWU ASR / Local CWU rep | 2
3 | 15 | N/A | 14 | Get the unit ready for all the Indoor changes (Site Preparation) | Site visit attendees invited (DOM, CWU Local Rep & ASR, Project Manager and MTC). Standard Agenda issued | Task 14a - DP Indoor work method improvement Start Up Meeting Agenda [C] | Task 14d - DP Indoor method improvement Agenda for Workshop [R] |  |  |  | Project Manager | Regional Lead | 4
4 | 17 | N/A | 15 | The Units Indoor work method improvement design (Site Design) | Current layout produced | Task 15a- DP Excel Floor Planning Tool to Use [C] | Task 15c - How to Use the Excel Floorplanning Tool Guide [R] |  |  |  | Project Manager | Planner / DOM / CWU ASR / Local CWU rep | 12
5 | 15 | N/A | 16 | Get the unit ready for all the Indoor changes (Site Preparation) | IWT validated with accurate current Hours and IWT updated to v7.4 | Units IWT | Task 05 - IWT Userguide and Update instructions [R].zip |  |  |  | Planner |  | 10
6 | 15 | N/A | 16 | Get the unit ready for all the Indoor changes (Site Preparation) | Current Office Indoor Performance understood | Units IWT |  |  |  |  | DOM | Project Manager / Planner | 3
7 | 16 | N/A | 20 | The Units Indoor work method improvement design (Site Design) | IPS Frame Requirement Understood - Frame Indicator completed and space requirements taken int | Task 20a - DP Sorting Frame Requirement Indicator Guidelines v2.0 [R] | Task 20b - DP Sorting Frame Requirement Indicator Master v2.0 (C) |  |  |  | Project Manager | Planner / DOM | 2
8 | 16 | N/A | 22 | Site Visit from the Key 'stakeholders' of the Indoor work method improvement changes. | Site Visit meeting held | Task 22a - DP Floorplanning Checklist v2 [CA] | Task 22b - DP Indoor work method improvement space standards v1.4 Final [R] |  |  |  | Project Manager | Planner / DOM / CWU ASR / Local CWU rep | 3
| 16 |  |  |  | Unit Risk assessment reviewed and building safety requirements understood, The space standards begin to formulate the process of the Layout. | Task 22c - DP SAC3 Unit pre deployemnt Q set Jan 2011 [C] | Task 22d - DP Unit Risk Assessment Review [C] |  |  |  | DOM | Planner / DOM / CWU ASR / Local CWU rep | 4
| 16 |  |  |  | Project Manager to take Pre photographs of the site and hold them on sharepoint site and display for journey of change | Task 22f - DP Indoor Pre method improvement Photograph List [CA] |  |  |  |  | Project Manager |  | 1
9 | 17 | M1 | 23 | The Units Indoor work method improvement design (Site Design) | Layout proposals discussed and agreed with DOM, CWU ASR and Local CWU rep (MTC scoping review) | Task 23a- DP Excel Floor Planning Tool to Use [C] | Task 23b - DP Indoor work method improvement space standards v1.4 Final [R] |  |  |  | Project Manager | Planner / DOM / CWU ASR / Local CWU rep,& MTC | 3
10 | 17 | N/A | 25 | The Units Indoor work method improvement design (Site Design) | Revised DRAFT Layout produced in Excel format and submitted to NDC | as above | as above |  |  |  | Project Manager | Planner / DOM / CWU ASR / Local CWU rep | 12
11 | 17 | M2 | 25 | The Units Indoor work method improvement design (Site Design) | PDF received from NDC and confirmed as correct and 'frozen' by returning the email confirming NDC's Layout | PDF of proposed unit layout from NDC |  |  |  |  | Project Manager | Planner | 2
12 | 19 | N/A | 27 | Clean Up and tidy the Unit | Review and plan the delivery Office clean up | [5 empty] | Project Manager | Planner | 8
13 | 17 | M3 | 28 | The Units Indoor work method improvement design (Site Design) | MTC costs received and reviewed and attached to Gleeds site. | N/A | N/A |  |  |  | MTC | Project Manager | 3
14 |  | N/A | 31 | The Units Indoor work method improvement design (Site Design) | Regional Sign off of layout, FM Works Programme and costs, C&D Director, DSM, DOM | Task 31a - DP Unit Indoor work methods Layout Sign off [CA] | Task 31b - DP SAC1 v2.5 (for building and Refurbishment work) [CA] |  |  |  | Project Manager | C&D Director / DSM / DOM / MTC / CWU ASR & Local CWU Rep | 4
15 |  | M4 | 33 | The Units Indoor work method improvement design (Site Design) | Layout and FM works agreed and approved, along with your equipment request by the Central Lead | email from Central lead | insert email into Task 31a - DP Unit Indoor work method improvement Layout Sign off [CA] |  |  |  | Central Lead | MTC / Project Manager | 2
16 | 21 | M5 | 34 | Request the new Indoor method improvement equipment for your unit | Equipment Request Submitted by MTC on Gleedsspace | N/A |  |  |  |  | MTC | PM / Central Project Assets / Gleeds | 2
17 | 18 | N/A | 35 | Involving / informing the staff about the Indoor changes (Staff Engagement) | DOM trained to deliver and subsequently presents Indoor improvement engagement to staff | [5 empty] | DOM | Project Manager / Planner / PTM | 24 | bar: 2011-10-19
18 | 18 | N/A | 45 | Involving / informing the staff about the Indoor changes (Staff Engagement) | Indoor Performance Measurement & Display implemented | Task 45a - DP Measurement and Display Slides [R] | Task 45b - DP Tracked and SD Measurement and Display chart [C] | Task 45c - DP Manual Measurement and Display Boards_v1.0 [C] | Task 45d - DP Where to find Planned Actual Performance data within IWT for Display v1.0 [R] | Task 45e - DP Daily Huddles Guidance [R] | DOM | Local CWU Rep | 4
19 |  | N/A | 46 | Preparing to deploy the New Indoor Layout | Produce labels for new IPS frames where applicable | Task 46a - IPS Fillets - Best Practice Examples [R] |  |  |  |  | DOM | Planner | 8
20 | 22 | N/A | 47 | Preparing to deploy the New Indoor Layout | Staff made aware of new IPS methodology (Porter Trolley Backless Frames and Mini York). The How to use a Backless Frame and Porter Trolley Poster Displayed. | Task 47a - DP SSOW IPS Backless FrameTrolley V1.5 Final [R] | Task 47b - DP York Safe System Of Work v2.3 [R] | Task 47c - DP Training Frame-Trolley1.1 [R] | Task 47d - DP Work Equipment Risk Assessment [C] |  | DOM | Project Manager / Planner | 8 | bar: 2011-10-19
21 | 22 | N/A | 48 | Preparing to deploy the New Indoor Layout | Office Risk Assessment updated following layout changes and the SAC 3 questions relating to 'Indoor method improvement' completed | Task 48a - DP SAC3 Unit pre deployemnt Q set Jan 2011 [CA] | Task 48b - DP Workplace Risk Assessmemt Manual WP1 [C] | Task 48c - DP First Aid Risk Assessment v 2.3 [C] | Task 48d - DP Fire Risk Assessment Guidance [R] | Task 48e - DP Fire Risk Assessment Review [C] | DOM | Safety team, ASR and Local CWU Rep | 2 | bar: 2011-10-19
22 | 22 | M6 | 65 | Deploy the New Indoor work method improvements and Facilities Management (FM) Works | Confirm the FM works completed including interim line markings. Revised Indoor Layout deployed ensure you have confirmed the change date with the MTC. | Task 65a - DP Delivery Office FM Works Completion sign off [CA] | Task 65b - DP Example Method Statement [R] | Task 65c - DPJob completion sheet vers 0.2 [R] |  |  | DOM | Project Manager / Gleeds / MTC | 4 | [14 empty] | To be completed on the weekend of change | bar: 2011-10-19
23 | 35 | N/A | 66 | Deploy the New Indoor work method improvements | IPS Sorters and Porters deployed. Staff Coached | Task 66a - DP SSOW IPS Backless FrameTrolley V1.5 Final [R] | Task 66b - DP York Safe System Of Work v2.3 [R] | Task 66c - DP Training Frame-Trolley1.1 [R] |  |  | DOM | Project Manager / Planner / Unit Line Managers | 8 | bar: 2011-10-19
24 | 137 | N/A | 106 | Performance Evaluation Review | Re-assess layout and office performance and complete the SAC 3 if you are only making Indoor work method changes to your Unit | Task 106a - DP Indoor work method improvement PER [CA] | Task 106b - DP Final Layout Changes [R] | Task 106c - DP SAC3 Unit Post deployment Q set Jan [C] |  |  | DOM/Project Manager / DSM | Project Manager / CWU & Local CWU Rep | 2 | bar: 2011-11-16 to 2011-11-23
25 | 60 | N/A | 144 | Record the changes that have been made to your unit. | Post Indoor change Photographs taken | Task 144c - DP Post work method improvement Photograph List [CA] |  |  |  |  | MTC | Project Manager / Planner | 2 | bar: 2011-12-28
26 | 83 | N/A | 150 | Final Local Concurrence | Delivery Manager works completion concurrence completed | Task 150b - DP Indoor work method improvements deployed Sign off [CA] |  |  |  |  | Project Manager |  | 2 | [15 empty] | 2011-12-28: indoor flow only
[12 empty] | Total Hours | 141
Note on H9: Subject to space and alignment to Standards