## 21 SWW PIR for reference (hidden)
Preston Plant
Preston Plant
Name |  | Simon Wilson |  |  | Date Implemented
Email |  | simon.x.wilson |  |  | SWW Wk 14 (June 28th 2021)
Section 1: Planned Savings
2014-01-01
Realignment Hrs Target | Actual Savings Achieved |  |  |  |  | Variance | Reasons for Variance. Include follow-up actions in Section 4.
| Ordinary | Casuals | SA | OT | Total Hrs Assured by FBP.
290 | 240 |  | 50 |  | 290 | 0
WIPWH Target | Actual WIWPH achieved. Assured by FBP. |  |  |  |  | Variance | Reasons for Variance. Include follow-up actions in Section 4.
126 | 128 |  |  |  |  | 2
Fixed Cost % Target | Actual Fixed Cost Achieved. Assured by FBP. |  |  |  |  | Variance | Reasons for Variance. Include follow-up actions in Section 4.
80% | 83%
Pir Period (4 to 6 Weeks) |  |  | Start Date | End Date | Total Days in PIR Period
|  |  | 2021-06-21 | 2021-08-01 | 41
Section 2: Workplan
|  | 99.9% | 99.5% | 99.9% | 99.5%
Pre |  |  |  | Post |  |  | Reasons if Workplan not met. Include follow-up actions in Section 4
Weeks used |  |  | Wk9-13 | Weeks used |  | Wk14-18
2c Meter & DSA processed by 22:00 |  |  | OK | 2c Meter & DSA processed by 22:00 |  | OK
All 2c Bags tipped to have 1c extracted before final despatch |  |  | OK | All 2c Bags tipped to have 1c extracted before final despatch |  | OK
100% Tracked 48 processed and ready for despatch by 10:00 |  |  | 77% | 100% Tracked 48 processed and ready for despatch by 10:00 |  | 79% | Current low traffic levels impacting on ability to fully resource advancement as planned.
Minimum 30% advancement of 2c mails by 6am |  |  |  | Minimum 30% advancement of 2c mails by 6am
Minimum 50% advancement of 2c mails by 10am despatch |  |  |  | Minimum 50% advancement of 2c mails by 10am despatch
Minimum of 60% of all available mail 90 mins prior to mains dispatch to be despatched |  |  | 11.73% | Minimum of 60% of all available mail 90 mins prior to mains dispatch to be despatched |  | 19.1%
Early Shift Workplan Clearance |  |  | Number of workplan Failures | Early Shift Workplan Clearance |  | Workplan failures now reduced
Late Shift Workplan Clearance |  |  | Number of workplan Failures | Late Shift Workplan Clearance |  | Workplan failures now reduced
Night Shift Workplan Clearance |  |  |  | Night Shift Workplan Clearance |  | Workplan failures now reduced | 06:15 finish time builds in contingency for late network arrivals. End state DTS also factored in
Page 1
Section 3: Planning Process Lessons Learnt
Phase 1 - Getting Started
Positive |  |  |  | Negative
The planning approach, using the Realignment Project Plan, was a very logical and straightforward route map. |  |  |  | The initial targets (WIPWH/GH) supporting the Project Plan increased due to revised Weightings being published. This undermined relationships and trust with the trade union in the short-term.
Phase 2 - Design
Positive |  |  |  | Negative
The Design phase prompted a reality check and moment of clarity for the management population as it exposed the underlying performance issues at a work area level. In summary the understanding of current performance differred from the Flighpatch challenge and came as a shock which kick started performance improvement activity in each work area. |  |  |  | The Base Data gathering activity particularly the Industrial Engineering style sampling / distance measurements, could have been better sign-posted. The local data gathering is now being challenged as a result of the lack of clarity and short timeframe given at the time.
Phase 3 - Deployment
Positive |  |  |  | Negative
The new streamlined approach to recruitment really helped expedite the process. The recent Workload Shock coupled with the full support of the trade union has helped communicate work area performance expectations. |  |  |  | Managing frontline expectations in terms of increasing contractual hours in the face of plummetting workload.
Section 4: Actions from PIR to feed into the Resourcing Process
Action |  |  |  | By Who | Planned Completion Date | Actual Completion Date
Concurrences and Sign-off
Plant Manager Concurrence
I am satisfied that the project is complete and that full accountability for maintaining the levels of
performance against national workplan is understood & managed in the line
Project Role
Name |  |  | Simon Wilson
Job Title |  |  | Plant Manager
Date
Area CWU Rep Concurrence
I am satisfied that the project as met the terms of reference and is fit for purpose
Project Role
Name |  |  | Saqib Parves
Job Title |  |  | Area CWU Processing Rep
Date
Finance Concurrence
I am satisfied that the project as met the hours and efficiency improvement and is fit for purpose
Project Role
Name |  |  | Lee Roger
Job Title |  |  | Senior Performance Manager
Date
SDL Sign Off
I am satisfied that the project is complete and has delivered the objectives set out above
Name |  |  | Steve Selby
Job Title |  |  | Service Delivery Leader
Date
Yes
No
Page 3
Note on A3: Use dropdown to choose office
Note on D22: Pre Revision weeks used for quality figures
Note on G22: Post Revision weeks used for quality figures

## PIR
Section 1: Plant Details
Unit
Unit Manager
Area CWU Rep
Date realignment implemented
Date PIR completed
Section 2: Optimised Duty Set
Summary of Assurance of duty set against model week workload (work hours only)
Demand hours (model workload) | Supply hours |  |  |  | Variance | Comments
| AWD | SA | Variable | Total Supply | Variance
|  |  |  | 0 | 0
Alignment of hours to model workload by shift and day
Comments
Assessment of productivity (WIPWH)
Target | Model week plan | Rebased target | Week 11 | Week 12 | Week 13 | Comments (add follow-up actions to Section 5)
Variance: | 0 | Variance: | 0 | 0 | 0
Assessment of fixed/variable %
Fixed % Target | Model week plan |  | Week 11 | Week 12 | Week 13 | Comments (add follow-up actions to Section 5)
85%
Variance | 85% |  | 85% | 85% | 85%
Section 3: Workplan and Quality
|  | 99.9% | 99.5% | 99.9% | 99.5%
Questions (as used during Assurance of duty set)
[5 empty] | Answer | Comments
Do your plans ensure all 2c / T48 mails are despatched only on the recognised 2c outlets?
Does your DSA duty set ensure that all DSA mails automation mails are processed to batch level by 22:00 to support the 83% target?
Does your duty set ensure all 2c bags are tipped and prepped ensuring 1c mails found achieve 1c despatch?
Does your duty set ensure that 100 % of T48 is processed and despatched by 10:00 (mains 2c despatches)?
Does your duty set ensure that all 2c meter mails as a minimum are processed through IMP/iLSM in time to extract all 1c mails and connect mails to 1c despatch?
Does your duty set ensure that Intra Manual Mails are sorted to Delivery Unit level in time to extract all 1c Missorts and connect to 1c despatch?
Does your duty set ensure that the minimum levels of In Process quality checks take place on every shift every day with appropriate input to SharePoint?
Does your duty set have containment resource aligned to known process point quality risk areas eg. hazards?
Does your production plan ensure that all parcels arriving 90 mins before mains despatches connect with mains 1c despatches?
Is there a plan in place to ensure skills are sufficient to execute a quality clearance following the realignment?
Section 4: PIR Concurrences
I am satisfied that the PIR is complete and that full accountability for maintaining the levels of performance against national workplan is understood & managed in the line
Plant Concurrence
Name
Job Title
Date
CWU Concurrence
Name
Job Title
Date
Section 5: Actions to complete following PIR
Action |  |  |  | By Who | Planned Completion Date | Actual Completion Date
EXAMPLE TO BE REPLACED
Note on C13: excluding reserves
Note on B14: from column D of "WIPWH for PIR" file
Note on D16: snip table from production control assurance and paste below
Note on D32: All WIPWH were rebased in P12 to reflect annual Planning Value refresh.
Note on B33: from column E of "WIPWH for PIR" file
Note on D33: from column F of "WIPWH for PIR" file

## Review of vacancies and supernu
Section A: Plant Details
Unit |  |  | 0
Unit Manager |  |  | 0
Area CWU Rep |  |  | 0
Date review completed
Date duty selection process completed
Section B: Review of vacancies and supernumeraries
Pre-Review | Supernumeraries |  | Vacancies |  |  | Summary of changes made as result of review
Shift | Heads | Hours | Duties | Hours
Early
Late
Night
Weekend
Total | 0 | 0 | 0 | 0
Post-Review | Supernumeraries |  | Vacancies
Shift | Heads | Hours | Duties | Hours
Early
Late
Night
Weekend
Total | 0 | 0 | 0 | 0
Variance | Supernumeraries |  | Vacancies
Shift | Heads | Hours | Duties | Hours
Early | 0 | 0 | 0 | 0
Late | 0 | 0 | 0 | 0
Night | 0 | 0 | 0 | 0
Weekend | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0
Section C: Workplan and Quality
Questions
[5 empty] | Answer | Comments
Do your plans ensure all 2c / T48 mails are despatched only on the recognised 2c outlets?
Does your DSA duty set ensure that all DSA mails automation mails are processed to batch level by 22:00 to support the 83% target?
Does your duty set ensure all 2c bags are tipped and prepped ensuring 1c mails found achieve 1c despatch?
Does your duty set ensure that 100 % of T48 is processed and despatched by 10:00 (mains 2c despatches)?
Does your duty set ensure that all 2c meter mails as a minimum are processed through IMP/iLSM in time to extract all 1c mails and connect mails to 1c despatch?
Does your duty set ensure that Intra Manual Mails are sorted to Delivery Unit level in time to extract all 1c Missorts and connect to 1c despatch?
Does your duty set ensure that the minimum levels of In Process quality checks take place on every shift every day with appropriate input to SharePoint?
Does your duty set have containment resource aligned to known process point quality risk areas eg. hazards?
Does your production plan ensure that all parcels arriving 90 mins before mains despatches connect with mains 1c despatches?
Is there a plan in place to ensure skills are sufficient to execute a quality clearance following the review?
Section D: Actions to complete following Review
Action (examples to be amended/deleted/added to as needed) |  |  |  | By Who | Planned Completion Date | Actual Completion Date
Update 318s in MDS
submit new TM1
update RCS
Submit OCRs
Submit ECRs
Update PSP work schedules
Submit MTSF proforma
Submit HR17s
Note on B9: Joint Statement: "Review of all workload aligned to current vacant duties or agency resource will take place to facilitate solutions to address the levels of stranded hours in each plant."
Note on D12: enter as decimals
Note on F12: enter as decimals

## LISTS (hidden)
ABERDEEN MC
BELFAST WBC
BIRMINGHAM MC
BRISTOL MC
CARDIFF MC
CARLISLE MC
CHELMSFORD MC
CHESTER MC
CROYDON MC
DORSET MC
EDINBURGH MC
EXETER MC
GATWICK MC
GLASGOW MC
GREENFORD MC
HOME COUNTIES NORTH MC
INVERNESS MC
JUBILEE MC
LEEDS MC
LONDON CENTRAL MC
MANCHESTER MC
MEDWAY MC
NORTH WEST MIDLANDS MC
NORTHERN IRELAND MC
NORWICH MC
NOTTINGHAM MC
PETERBOROUGH MC
PLYMOUTH MC
PRESTON MC
PRINCESS ROYAL DC
ROCHESTER WBC
ROMFORD MC
SCOTLAND DC
SCOTTISH WBC
SHEFFIELD MC
SOUTH MIDLANDS MC
SOUTH WEST DC
SOUTHAMPTON MC
SWANSEA MC
SWINDON MC
SWINDON WBC
TRURO MC
TYNESIDE MC
WARRINGTON MC
WARRINGTON RAIL TERMINAL
WARRINGTON WBC
YORKSHIRE DC