## Overview
RM Peak 2025 Summary Report
Project Types | Total | Additions | Scoped | Priced | Awaiting Pricing | No Works | Aborted | Instructed | Awaiting Instruction | Programmed | Status / Comments
Outhouses | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 5 | Livingston - H/O to Ops. Dock Levelles installed. Snags/additiona works being completed.
NI OH - cost agreed, site acquired. Asbestos remediation by landlord. Building works on track Yard ongoing.
Northampton Outhouse - handed over.
Norwich Outhouse - works completed
Bristol Outhouse (Cardiff) - handed over
Internals | 6 | 1 | 7 | 6 | 0 | 0 | 1 | 6 | 0 | 6 | Sheffield, MK, Atherstone, Chelmsford all approved and instructed. Atherstone, MK., Sheffiled completed.
Exeter works delivered alongside marquee installation - approved & instructed
No works required at ELDC
York Parcel Hub added - on site
Marquees | 21 | 3 | 21 | 23 | 0 | 0 | 3 | 21 | 0 | 21 | Glasgow G15 & Bude added - 19/09. Price/Porgramme issued - approved
Patchway added - Accio plan/price issued for approval - not required
All other marquees approved, instructed and programmed in
South Midlands and Colchester aborted
VOC Sites | 9 | 0 | 9 | 6 | 0 | 3 | 0 | 6 | 0 | 6 | PRDC, HWDC, SDC, SWDC, Carlisle approved & instructed. Landlord's works at PRDC to be inspected.
NI VOC agreed scope approved. 655 Antrim Road only.
PFW | 5 | 0 | 4 | 4 | 0 | 1 | 0 | 3 | 0 | 4 | Camberley, York and Totenham instructed and on site
Glasgow - Renfrew site to be used again.
Birmingham - no works, PFW using Relay site, Wednesbury

## Outhouses
ROYAL MAIL XMAS 25/26 - OUTHOUSES
REFS | DETAILS |  |  |  |  | SURVEYOR |  |  | RFS / LDS DATES |  | SCHEDULE OF CONDITION |  | APPROVALS |  |  |  | PROGRAMME
| SITE | ADDRESS | RFS Status | Update | Decisions/Actions | PRACTICE | SURVEYOR 2 | Previous Surveyor | RFS | LDS | INSPECTION | ISSUED | INSPECTED ON | PRICE ISSUED | RM APPROVED | INSTRUCTED | COMMENCEMENT ON SITE | HANDOVER DATE | DILAPS START | DILAPS END
Site 1 | Norwich Outhouse | Bay 2, Diamond Road, Norwich, NR6 6AN |  | Accio/Vinci costs received. Vinci costs challenged and updated. Revised cost issued to LG for review/approval.. RFS date brought forward a week to 10/11/25 Vinci cost approved. | Temporary dock and ceiling tile details to be approved by landlord. | RLB |  |  | 2025-11-10 | 2025-12-23 | 2025-08-07 | 2025-08-23 | 2025-08-07 | 2025-09-04 | Accio cost approved - 18/09/25 Vinci cost approved - 25/09/25 | 2025-09-25 | 03/11/2025 Accio 05/11/25 | 2025-11-07 | 2026-01-05 | 2026-01-09
Site 2 | NI OH | UNIT22a , KILROOT BUSINESS PARK, CARRICKFERGUS |  | Build up of parking area - CBR test undertaken results received - original proposal ratified. Contamination of yard (ex fuel store area) - testing undertaken - samples returned results are all within normal levels. No asbestos information for building - survey done by Tetra tech - asbestos identified to pipework. No RAAC info available - survey completed - no RAAC. Kingsway costs for works received. Dock Leveller report& Asbestsos report received - completed by landlord | Works to be completed to building Yard ongoing. | AECOM |  |  | 2025-10-24 | 2026-01-18 | 2025-09-09 | 2025-09-10 | 2025-07-23 | 2025-09-12 | 2025-09-22 | 2025-09-24 | 2025-10-06 | 2025-10-24
Site 3 | Livingston | UNIT 6, ROYSTON ROAD, DEANS INDUSTRIAL ESTATE, DEANS, LIVINGSTON, EH54 8AL |  | Site has had a break in - considerable reinstatment needed. Asbestos remediation - 2no LARCS engaged to speed up removal Dock Levellers - instruction to install 12no new levellrs, awaiting programme WCs/Welfare provision - required areas identified Peak costs issued for approval 04.09 - approved Costs for temporary power issued 05.09 - approved. Dock Leveller install dates provided. Generator to be installed for power. | Cost allocated & recorded - - ongoing (Asbestos/Peak/Security/Reinstatement) for loss adjuster Finalise external line marking works | RLB |  |  | 2025-11-03 | 2026-01-18 | N/A | N/A | various dates pre & post break in | Dock Levellers - 28/08/25 Peak - 04/09/25 Temp power - 05/09/25 Reinstatement - ongoing | Dock Levellers - 28/08/25 Temp power - 05/09/25 Peak - 12/09/25 | Dock Levellers - 28/08/25 Temp power - 05/09/25 Peak - 12/09/25 | 2025-09-08 | Ops in 27/10 RFS 03/11 Dock levellers - 07/11
Site 4 | Bristol Outhouse (Cardiff) | Lakeside, Fountain Lane,St Mellons, Cardiff, CF3 0FB |  | Site has had a break in - AN has been raising helpdesk requests, intention to get all done by end of the month before Security leave site. Meeting with the SEP on 04/09 to scope Peak works. Scope/costs approved, contractor instructed. | Scope/costs approved - works to be completed. | KKS |  |  | 2025-11-10 | 2025-12-24 | N/A | N/A | 2025-09-04 | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-22 | 2025-10-28
Site 5 | Northampton Outhouse | Unit 1, Panattoni Park, Weedon Road, NN7 4GP |  | External cladding/signage - planning application submitted 28/08 - decision will be after RFS date - due to landlord consent issue Building control application submitted. | Design for temporary heating to be implemented. Planning consent for signage will not arrive in time - temporary RM signage to be installed. Temporary Lighting for yard to be provided. | RLB |  |  | 2025-11-03 | 2026-01-18 | N/A | N/A |  |  |  | Phase 2 29/08/25 | Phase 2 15/09/2025 | Phase 2 24/10/2025
Note on R4: Paul McGouran: Add planned start if not commenced
Note on S4: Paul McGouran: Add planned date if not complete

## Internals
ROYAL MAIL XMAS 25/26 - INTERNALS
REFS | DETAILS |  |  |  |  | SURVEYOR |  |  | APPROVALS |  |  |  | PROGRAMME
| SITE | ADDRESS | RFS Status | Update | Decisions/Actions | PRACTICE | RFS | LDS | INSPECTED ON | PRICE ISSUED | RM APPROVED | INSTRUCTED | COMMENCEMENT ON SITE | HANDOVER DATE | DILAPS START | DILAPS END
Site 1 | Chelmsford MC | Chelmsford Mail Centre, Winsford Way, Chelmsford, CM2 5AA |  | Quote for temporary floor issued and approved. | Works to proceed | RLB | 2025-11-10 | 2026-01-05 | N/A | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-11-07 | 2025-11-09 | 2026-01-06 | 2026-01-08
Site 2 | Exeter MC | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX |  | Works in conjunction with marquee - KKS have in hand | Works included in marquee install and approved alongside marquee proposal | KKS | 2025-11-03 | 2025-12-31 | N/A | 2025-07-29 | 2025-08-13 | 2025-08-14 | 2025-10-30 | 2025-11-02 | 2026-01-06 | 2026-01-09
Site 3 | Sheffiled Manton Outhouse | Manton 70, Manton Wood Industrial Estate, Worksop S80 2RS |  | Cost proposal issued for approval. Upadted cost issued and approved | Instruct contractor and complete the works | RLB | 2025-10-27 | 2026-01-10 | 2025-08-12 | 29/08/2025 08/09/25 | 2025-09-12 | 2025-09-15 | 2025-10-20 | 2025-10-25
Site 4 | Milton Keynes PSC | MK PSC , Magnitude 314, Magna Park, Milton Keynes MK17 8EW |  | Cost proposal issued for approval Feedback received - costs to be updated and reissued. Approved | Instruct contractor and complete the works | RLB | 2025-11-03 | 2026-01-10 | 2025-08-22 | 2025-08-29 | 2025-09-15 | 2025-09-15 | 2025-10-13 | 2025-10-17
Site 5 | Atherstone PSC | 15 Carlyon Road, Atherstone, CV9 1LQ |  | Cost proposal issued for approval Feedback received - costs to be updated and reissued.Approved | Instruct contractor and complete the works | RLB | 2025-10-20 | 2026-01-10 | 2025-08-14 | 05/09/2025 08/09/25 | 2025-09-12 | 2025-09-15 | 2025-10-06 | 2025-10-10
Site 6 | ELDC - dual use with ADM C East | Gardeners way, Oliver Road, Grays, RM20 3ED |  | Site visit to scope works completed 02/09. SoW reviewed & revised | No works required. No longer a Peak site. | RLB | n/a | n/a | n/a | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Site 7 | York Parcel Hub | SILKSTONE HOUSE, EXPRESS WAY, NORMANTON WF6 2XX |  | New request | Instruct contractor and complete the works | RLB | 2025-11-24 | n/a | 2025-10-13 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 2025-11-05 | 2025-11-24 | N/A | N/A
Note on N4: Paul McGouran: Add planned start if not commenced
Note on O4: Paul McGouran: Add planned date if not complete

## Marquees
ROYAL MAIL XMAS 25/26
REFS | DETAILS |  |  |  |  | SURVEYOR | RFS/LDS DATES |  | APPROVALS |  |  | PROGRAMME
| SITE | ADDRESS | RFS Status | Update | Decisions/Actions | PRACTICE | RFS | LDS | PRICE ISSUED | RM APPROVED | INSTRUCTED | COMMENCEMENT ON SITE | HANDOVER DATE | DILAPS START | DILAPS END
Site 1 | Jubilee MC | Jubilee Mail Centre, Godfrey Way, Hounslow, TW4 5XX |  | Plan/cost issued for approval Reverting to 2024 option - approved |  | KKS | 2025-11-10 | 2026-01-16 | 08/08/2025 Revised issued - 15/09/25 | 2025-09-15 | 2025-09-15 | 2025-11-02 | 2025-11-09
Site 2 | Swansea MC | Swansea Mail Centre, Siemens Way, Swansea, SA1 1AA |  | Approved |  | KKS | 2025-11-03 | 2025-12-29 | 2025-08-14 | 2025-08-22 | 2025-08-23 | 2025-10-28 | 2025-10-31
Site 3 | Carlisle Plant | Carlisle Mail Centre, Junction Street, Carlisle , CA1 1AA |  | Approved |  | JYM | 2025-10-27 | 2025-12-24 | 2025-07-29 | 2025-08-13 | 2025-08-14 | 2025-10-17 | 2025-10-24 | 2026-01-05 | 2025-01-09
Site 4 | Tyneside Mail centre | Tyneside Mail Centre, Lindisfarne House, Earlsway, TVTE, Gateshead, NE110YY |  | Approved |  | RLB | 20/10/2025 | 25/12/2025 | 2025-07-29 | 2025-08-22 | 2025-08-23 | 2025-10-10 | 2025-10-16
Site 5 | Romford MC | Romford Mail Centre Queen, Elizabeth House, Sandgate Close, ROMFORD, RM7 0AB |  | Approved Revised RFS and Install dates |  | RLB | 2025-11-21 | 2026-01-05 | 25/07/2025 Additional plans/costs to be issued | 2025-08-22 | 2025-08-22 | 2025-11-16 | 2025-11-20
Site 6 | Swindon MC | RM Swindon MC, Rowland Hill Close, Dorcan, SN3 5TQ |  | Approved |  | KKS | 2025-11-17 | 2026-01-05 | 2025-07-29 | 2025-08-13 | 2025-08-14 | 2025-11-07 | 2025-11-14
Site 7 | Southampton MC | SOMC - Mitchell Way - SO18 2XX |  | Approved |  | KKS | 2025-11-11 | 2026-01-05 | 2025-08-14 | 2025-08-22 | 2025-08-23 | 2025-11-05 | 2025-11-07
Site 8 | Medway MC | 1 Knight Road, Rochester, ME2 2EE |  | Approved Subsequently RM have asked Accio to consider positioing of marquee - to be reviewed on site and positioned accordingly. |  | RLB | 2025-11-03 | 2026-01-05 | 2025-07-29 | 2025-08-22 | 2025-08-23 | 2025-11-02 | 2025-11-02
Site 9 | Dorset Mail Centre | Dorset Mail Centre, Nuffield Industrial Estate, Poole, Dorset, BH17 0AA |  | Approved |  | KKS | 2025-11-03 | 2026-01-03 | 2025-07-25 | 2025-08-13 | 2025-08-14 | 2025-10-26 | 2025-10-29
Site 10 | Exeter Mail Centre | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX |  | Approved |  | KKS | 2025-11-03 | 2025-12-31 | 2025-07-29 | 2025-08-13 | 2025-08-14 | 2025-10-30 | 2025-11-02
Site 11 | Truro Mail Centre | Truro Mail Centre, Newham Road, Truro, TR1 1AA |  | Approved |  | KKS | 2025-11-10 | 2025-12-24 | 2025-07-29 | 2025-08-13 | 2025-08-14 | 2025-11-03 | 2025-11-04
Site 12 | Croydon MC | 36-40 Factory Lane, Croydon, CR0 3RL |  | Approved |  | RLB | 2025-11-11 | 2026-01-05 | 2025-07-25 | 2025-08-13 | 2025-08-14 | 2025-10-30 | 2025-11-06
Site 13 | Nottingham MC | Padge Road, Beeston, Nottingham, NG9 2RR |  | Incorrect plan issued by Accio 02/09. Reissued on 03/09 - Approved |  | RLB | 2025-11-03 | 2026-01-05 | 2025-09-03 | 2025-09-08 | 2025-09-08 | 2025-10-23 | 2025-10-29
Site 14 | Inverness MC | Inverness Mail Centre, 50 Seafield Road, Inverness, IV1 1SG |  | Approved |  | RLB | 2025-11-03 | 2026-01-05 | 2025-07-25 | 2025-08-26 | 2025-08-26 | 2025-10-26 | 2025-10-30
Site 16 | Bridgend DO | Bridgend DO, Tremains Road, Bridgend, CF31 1ZZ |  | 8m x 10m marquee required - Accio to provide revised plan/quote. Electric heating requested - power to be provided. Plan/cost issued & approved |  | KKS | 2025-10-27 | 2026-01-03 | 2025-09-08 | 2025-09-10 | 2025-09-10 | 2025-10-24 | 2025-10-25
Site 17 | Cinderford DO | Cinderford DO, Woodside Street, Cinderford, GL14 2NQ |  | Approved |  | KKS | 2025-11-03 | 2025-12-24 | 2025-07-29 | 2025-08-22 | 2025-08-23 | 2025-11-01 | 2025-11-01
Site 18 | Buxton DO | Palace Road, Buxton, SK17 6AB |  | Approved |  | RLB | 2025-11-17 | 2026-01-04 | 2025-08-19 | 2025-08-20 | 2025-08-20 | 2025-11-13 | 2025-11-13
Site 19 | Huntingdon DO | Huntingdon Delivery Office, Penfold Court, Huntingdon, PE29 7AB |  | Approved |  | RLB | 2025-10-27 | 2026-01-05 | 2025-08-11 | 2025-08-26 | 2025-08-26 | 2025-10-23 | 2025-10-24
Site 21 | Oldham DO | 21 Hamilton Street, Oldham |  | Approved |  | RLB | 2025-11-17 | 2026-01-05 | 2025-09-05 | 2025-09-10 | 2025-09-10 | 2025-11-09 | 2025-11-09
Site 22 | G15 | Hecla Avenue, Glasgow, G15 8LY |  | Approved |  | RLB | 2025-11-06 | 2026-01-22 | 2025-09-18 | 2025-10-07 | 2025-10-07 | 2025-10-31 | 2025-11-04
Site 23 | Bude DO | Belle Vue, Bude, EX23 8LU |  | Approved |  | KKS | 2025-11-03 | 2026-01-06 | 2025-09-24 | 2025-10-07 | 2025-10-07 | 2025-11-03 | 2025-11-03
Site 24 | Patchway DO | Derwent Close, Bristol, BS34 5HZ |  | No longer required Removed from programme |  | RLB
Site 15 | South Midlands MC | Royal Mail South Midlands, Swan Valley Way, NORTHAMPTON, NN4 9DR |  | No longer required Removed from programme |  | RLB
Site 20 | Colchester DO | Colchester Delivery Office, Moorside, Colchester, CO1 2GB |  | No longer required Removed from programme |  | RLB
Note on M4: Paul McGouran: Add planned start if not commenced
Note on N4: Paul McGouran: Add planned date if not complete

## Parking VOC
ROYAL MAIL XMAS 25/26 - PARKING/VOC'S
REFS | DETAILS |  |  |  |  | SURVEYOR |  |  | SCHEDULE OF CONDITION |  | APPROVALS |  |  |  | PROGRAMME
| SITE | ADDRESS | RFS Status | Update | Decisions/Actions | PRACTICE | RFS | LDS | INSPECTION | ISSUED | INSPECTED ON | PRICE ISSUED | RM APPROVED | INSTRUCTED | COMMENCEMENT ON SITE | HANDOVER DATE | DILAPS START | DILAPS END
Site 1 | PRDC | Global House, Laxcon Close, Neasden, London NW10 0TG |  | Site visit undertaken to Global House. Scope issued - awaiting costs from Vinci. Costs issued and approved. Contratcor instructed. | Works to proceed | RLB | 2025-10-27 | 16/01/2026 | 2025-08-26 | 2025-09-05 | 2025-08-26 | 2025-09-10 | 2025-09-15 | 2025-09-17 | 2025-10-20 | 2025-10-25 | 2026-01-16 | 2026-01-30
Site 4 | NI VOC | Ballycraigy Business Park, 655 Antrim Road, Mallusk, BT36 4RG |  | Parking plans issued for both sites Scope/cost for lighting approved. | RM to advise on whether cabin needed | AECOM | 2025-10-27 | 2025-01-23 | 2025-09-09 |  | 2025-06-05 | 2025-09-15 | 2025-09-16 | 2025-09-19 | 2025-10-20 | 2025-10-25 | 2026-01-23 | 2026-01-30
Site 5 | SDC VOC | M8 Truckstop, Westfield Road, Newhouse Industrial Estate, Motherwell ML1 5TX |  | SoW /Cost issued & approved. SoC completed. | Works to proceed | RLB | 2025-10-20 | 2026-01-23 | 2025-09-04 | 2025-09-08 | 2025-05-07 | 2025-08-05 | 2025-08-05 | 2025-09-18 | 2025-10-15 | 2025-10-16 | 2026-01-23 | 2026-01-30
Site 6 | HWDC VOC | Prologis Park, 1 Iron Bridge Rd, Stockley, Uxbridge,UB11 1FP |  | Cost issued by Vinci but have been challenged by RLB. Revised cost issued for approval. Approved. Contractor instructed. | Works to proceed | KKS | 20/10/2025 RFS 10/11 - in line with O Licence | 16/01/2026 | 2025-08-28 | 2025-09-11 | 2025-08-13 | 2025-09-08 | 2025-09-18 | 2025-09-18 | 2025-10-13 | 2025-11-07 | 2026-01-16 | 2026-01-23
Site 8 | SWDC VOC | Plot W3/S8, Severnbanks, Central Avenue, Avonmouth Bristol BS10 7SD |  | SoC completed and issued. Scoping visit arranged for 08/09. Price issued, reviewed and approved. Contracor /instructed | Works to proceed | KKS | 2025-10-20 | 2026-01-23 | 2025-08-04 | 2025-08-12 | 2025-09-08 | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-10-13 | 2025-10-17 | 2026-01-23 | 2026-01-30
Site 9 | CARLISLE PAR | Apex Electrical Car Park (Former Newsquest), Shaddongate, Carlisle, CA2 5UA |  | Scope of works agreed. Landlord to provide lighting - included in terms of lease. SoC issued. | Progress works in conjunction with landlord | JYM | 2025-10-20 | 2025-12-24 | 2025-08-13 | 2025-08-20 | 2025-08-13 | 2025-08-13 | 2025-08-20 | 2025-08-22 | 2025-10-17 | 2025-10-20 | 2026-01-12 | 2026-01-12
Site 2 | COVENTRY VOC | Secland Group, Bedworth Road CV6 6HH |  | No works required - SoC issued | None | RLB | N/A | N/A | 2025-08-11 | 2025-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Site 3 | MSH VOC | Yard 12, Europark Industrial Estate, A5 Watling Street, Clifton-upon-Dunsmore, Rugby, CV23 0AL |  | No works required - SoC issued | None | RLB | N/A | N/A | 2025-08-11 | 2025-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Site 7 | MK VOC | Unit 410 Fen Street, Magna Park, MK17 8EW |  | No works required - SoC issued | None | RLB | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Note on P4: Paul McGouran: Add planned start if not commenced
Note on Q4: Paul McGouran: Add planned date if not complete

## Frames
ROYAL MAIL XMAS 25/26 - FRAMES
REFS | DETAILS |  |  |  | SUPPLIER |  | Dates to be ready for
| SITE | ADDRESS | RFS Status | Comments - same as 2024? | Frame Move Company | Contact | RFS | LDS
Site 1 | HCN MC | HCN MC, Maylands Avenue, Hemel Hemstead, HP2 7XX |  | TBC | Askona | Kirsty Cooper Haby Uppal | 2025-11-10 | 2026-01-05
Site 2 | Romford MC | Romford MC, Queen Elizabeth House, Sandgate Close, Romford, RM7 0AB |  | No - possible increase by 3 frames - Frames already in situ, unless an additional 3 frames are required, then all frames will need to be relocated | Askona | Kirsty Cooper Haby Uppal | 2025-11-10 | 2026-01-05
Site 3 | Norwich OH | Bay 2 Diamond Road, Norwich, NR6 6AN |  | No - Reduction | Askona | Kirsty Cooper Haby Uppal | 2025-11-10 | 2025-12-23
Site 4 | Greenford MC | Greenford MC, Green Park Way, Greenford, UB6 0GG |  | No | Askona | Kirsty Cooper Haby Uppal | 2025-11-10 | 24/12/2025
Site 5 | Bristol MC | Bristol MC, Gloucester Road North, Filton, Bristol, BS34 7ST |  | Yes | PH Tech | Kirsty Cooper Haby Uppal | 2025-11-17 | 2025-12-24
Site 6 | Dorset MC | Dorset Mail Centre, Nuffield Industrial Estate, Poole, Dorset, BH17 0AA |  | Yes | PH Tech | Kirsty Cooper Haby Uppal | 2025-11-10 | 2025-12-24
Site 7 | Exeter MC | Exeter Mail Centre, Osprey Road, Sowton Industrial Estate, Exeter, EX2 7XX |  | Yes | PH Tech | Kirsty Cooper Haby Uppal | 2025-11-17 | 2025-12-24
Site 8 | Swansea MC | Swansea Mail Centre, Siemens Way, Swansea, SA1 1AA |  | Frames to go into the marquee Marquee H/O date 31st Oct. | PH TECH | Richard Daniels | 2025-11-17 | 2025-12-24
Site 9 | Manton OH | Manton 70, Manton Wood Industrial Estate, Worksop S80 2RS |  | Yes | Askona | Kirsty Cooper Haby Uppal | 2025-11-17 | 2025-12-24
Site 10 | Sheffield MC, | Sheffield MC, Brightside, Sheffield, S9 2XX |  | Yes | Askona | Kirsty Cooper Haby Uppal | 2025-11-17 | 2025-12-24
Site 11 | South Midlands MC | Royal Mail Northampton PSC Unit 5 Panattoni Park Weedon Road NORTHAMPTON NN7 4DE |  | Yes | Askona | Kirsty Cooper Haby Uppal | 2025-11-24 | 2026-01-03
Site 12 | South Midlands PSC | Royal Mail South Midlands Swan Valley Way NORTHAMPTON NN4 9DR |  | Yes | Askona | Kirsty Cooper Haby Uppal | 2025-11-24 | 2026-01-03
Site 13 | Chester MC | Chester Mail Centre Jupiter Drive Chester CH70 8DF |  | Yes | PFS | Andy Swindells | 2025-11-15 | 2026-01-03
Site 14 | Tyneside MC | Tyneside Mail Centre, Earlsway, Gateshead NE11 0YY |  | Yes | Askona | Kirsty Cooper Haby Uppal | 24/11/2025 | 31/12/2025
Site 15 | Preston MC | Preston MC 4 Pitman Way Preston PR11 2BS |  | Yes | PFS | Andy Swindells | 2025-11-24 | 2025-12-24
Site 16 | Carlisle MC | Royal Mail Junction Street Carlisle CA1 1AA |  | Carlisle only need 4 frames brought into the Plant instead of 10 as 6 are already in situ. | PFS | Andy Swindells | 2025-11-24 | 2025-12-24
Site 17 | Nottingham MC | Padge Road, Beeston, Nottingham, NG9 2RR |  | Nottingham need frames put into to the side Marquee Marquee H/O 28/10/25 | Askona | Kirsty Cooper Haby Uppal | 2025-11-03 | 2026-01-05
Site 18 | Plymouth MC | Breakwater Road, Plymouth, PL9 7XX |  | Yes | PH Tech | Kirsty Cooper Haby Uppal | 2025-11-17 | 2025-12-24

## PFW
PARCELFORCE XMAS 25/26 - OUTHOUSES
REFS | DETAILS |  |  |  |  | SURVEYOR | RFS / LDS DATES |  | SCHEDULE OF CONDITION |  | APPROVALS |  |  |  | PROGRAMME
| SITE | ADDRESS | RFS Status | Update | Decisions/Actions | PRACTICE | RFS | LDS | INSPECTION | ISSUED | INSPECTED ON | PRICE ISSUED | PFW APPROVED | INSTRUCTED | COMMENCEMENT ON SITE | HANDOVER DATE | DILAPS START | DILAPS END
Site 1 | NORTH ESSEX CHR LD | London Tottenham IND, Units 6&7 Segro Park, N17 7RP |  | Units 1 & 2 required Site visit 16/09 to update SoW & SoC SoW/SoC issued. | Costs issued in line with requirements. Awaiting approval. | RLB | 2025-11-11 | 2025-12-24 | 2025-08-19 | 2025-09-22 | 2025-08-19 | 2025-09-26 | 2025-09-29 | 2025-09-29 | 2025-10-06 | 2025-10-31 | 2026-01-05 | 16/01/2026 (TBC)
Site 2 | GLASGOW CHR LD | 41 Balmoral Street, Scotstoun, Glasgow, G14 0HB |  | Awaiting costs for fit out SoC issued Landlord wants racking stored (not disposed) and have possibly reoved the cabin. | Update required on Balmoral St & Renfrew | RLB | 2025-10-31 | 2025-12-24 | 2025-09-05 | 2025-09-19 | 2025-09-02 | 2025-09-22 |  |  | 2025-10-13 | 2025-10-31 | 2026-01-05 | 2026-01-16
Site 3 | YORK CHR LD | York 36, Hunter Drive, Airfield BP, Elvington, YO41 4AU |  | Costs approved Checking on landlords works | Landlord to complete works Legals to be completed Works to proceed | RLB | 2025-11-11 | 2025-12-24 | 2025-08-14 | 2025-09-02 | 2025-08-14 | 2025-09-01 | 2025-09-16 | 2025-09-19 | 2025-10-13 | 2025-10-31 | 2026-01-05 | 2026-01-16
Site 4 | ALDERSHOT CHR LD (CAMBERLEY) | The Point, Watchmoor Road, Camberley, GU15 3AD |  | Costs approved Contractor instructed Waiting on legals | Legals to be completed Works to proceed | KKS | 2025-11-11 | 2025-12-24 | 2025-08-18 | 2025-08-26 | 2025-08-18 | 2025-09-10 | 2025-09-10 | 2025-09-19 | 2025-10-06 | 2025-10-31 | 2026-01-05 | 2026-01-16
Site 5 | BIRMINGHAM CHR LD | Relay - RM Wednesbury, Kings Hill Business Park, Royal Mail, Darlaston Rd, Wednesbury WS10 7DG |  | Site search aborted PFW to cohabitate with RM | No actions for RLB | RLB | 2025-10-06 | 2026-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Note on P4: Paul McGouran: Add planned start if not commenced
Note on Q4: Paul McGouran: Add planned date if not complete